## Slide 1
WS6 – Where We Are
Enabling Weekly LM Map Releases · March → May 2026
What we've delivered
✅
9 weekly releases
CW14–CW21, every week without a gap
✅
7 of 9 on time
On or before Thursday target
✅
First combined CARIAD + VOLVO release
CW17 — both endpoints live same week
✅
CARIAD confidence restored
Voluntarily skipped CW19 — a sign of trust
✅
New features shipped
Drive Path layer + 8 self-contained features (CW18)
✅
Incremental pipeline live
New mini-binding layer active; old one decommissioned
Lead time targets
NOW
~13.8 days
avg CW16–CW20
▼
End Q2 · External goal
≤ 11.5 days
⭐ Already hit it!
CW17: 10.61 days
▼
September · External goal
≤ 9 days
Incremental pipeline
▼
End of Year · Internal goal
≤ 7 days
Ready for CARIAD mid-'27
▼
🎯 North Star · mid-2027
CARIAD weekly cadence at scale
Momentum
Lead time per release (days)
13.82
CW15
14.44
CW16
10.61
CW17
13.81
CW18
13.77
CW20
Q2 target
⭐ CW17: 10.61 days
First time under Q2 target.
Proof that 11.5 days is achievable now.
Sources: W21 Confluence weekly report · WS6 main page (1505067229) · JIRA ADASHD-2672 · May 2026

## Slide 2
WS6 – Lead Time Improvement Roadmap (Goal 2)
May → September 2026 | Current: 13.77 days (CW20) | Target: 9.0 days (Q3)
May '26
Jun
Jul
Aug
Sep
To-Be process design
ADASHD-2756
Alignment
M. Aigner
Process telemetry
ADASHD-3336
Enables measurement
A. Jalali
Remove NDS.Live idle time
ADASHD-3339
−2.3 days
P. van Hulten
Tool automation / handoffs
ADASHD-3625
−0.5 days
A. Jalali
DevMap/Staging stability
ADASHD-2755
−0.5 days
T. Szambor
Incremental P0a: Crosslink
ADASHD-2764
−1.2 days
T. Bekaert
Incremental P0b: Lane Fn
ADASHD-2764
−2.0 days
E. Goraca
Incremental P1: Self-contained
ADASHD-2764
−0.8 days
D. Turobos
Today
7
8
9
10
11
12
13
14
15
Lead time (days)
Q2 target 11.5d
Q3 target 9.0d
Now 13.77d
−2.3d (NDS.Live idle)
−1.0d (automation + stability)
−1.2d (Crosslink incremental)
−2.0d (Lane Fn incremental)
−0.8d (P1 incremental)
Process / automation
Incremental processing